## 16.04.23
Section | Page | Item | Sub Item | Description | Reference | Platform | Type | Feedback/Bug/CR | Dev Status | Comments
Influencer | Edit Profile | Social Media Presence | Field Asterisks | Should be visible for mandatory fields |  | Both | Design & Functionality | CR
|  | Social Media presence | Submit | Without filling the mandatory fields user won't be able to submit the profile. Message will be shown identifying the issue. |  | Both | Design & Functionality | CR
Master Brand |  | Create Job |  | there will be predefined range. | Range: 10000-50000 50000-100000 100000-150000 150k+ | Both | Design & Functionality | CR | BE
All | Home Page | Sign Up | - | Sign up button will be visible in the home page |  | Both | Design & Functionality | CR | BE
|  | Edit Profile | - | Need to be visible & eye catching |  | Both | Design & Functionality | Feedback
|  | Profile Icon | - | edit profile , complete profile , logout functions will be included in this. Profile picture will be shown here as well. |  | Both | Design & Functionality | CR | BE + FE
| Home Page | Slider image | - | After transition there will be another picture |  | Both | Design | CR | BE + FE
|  | Images | - | Picture brushing should be implemented |  | Both | Design | Feedback
| Home Page | Cover Image | - | Neon coloured effect should be implied | https://drive.google.com/file/d/1UNPUYkWoVEV1WsTCAdpxly9rwnODTJSN/view?usp=share_link | Both | Design | CR
|  | What influencer say about us | - | Should be eye catching |  | Both | Design | CR
|  |  | - | Testimonials will be used as sliders. No video section will be there |  | Both | Design & Functionality | CR
|  | Testimonials | - | Background colour will be changed.Clicking on a specific testimonial will be changed to light green colour. other testimonials will be white. |  | Both | Design | CR
|  | Trusted by | - | Prominent Background |  | Both | Design | CR
|  | Benefits | - | Numbers will be light green or colour correction is needed |  | Both | Design | CR
All | Services | Dropdown | - | There will be another category in the dropdown named "Our Flagship Programs". Clicking on that will be redirected to a sub menu. ref : http://themarvel.com/ |  | Both | Design & Functionality | CR | BE
| Home Page | Be Marvel Be you | Cover Image | Position will be same as figma. Currently cover image overlaps with the text. |  | Both | Design & Functionality | Bug
|  | Get the latest news | Allignment | should follow figma | https://drive.google.com/file/d/1f1mV_TKuCzE3LRLvFQVq4yfMTuUzRX84/view?usp=share_link | Both | Design | Feedback
|  | Testimonials | Enayet Chowdhury | Design breaks. please keep the same background for all the testimonials | https://drive.google.com/drive/folders/1vmL09EypsgBjzenSB4O1E-r4nNH6BNOP?usp=share_link | Both | Design & Functionality | Bug
|  | Trsuted By | Cards | All cards should be clickable. | https://drive.google.com/drive/folders/1XndDgkMpTkuTC1EDE__7NApP4j1j4J08?usp=share_link | Both | Design | Bug
|  | Cover Video | - | Video upload option should be implemented from backend. Currently only youtube video uploading is allowed. | https://drive.google.com/file/d/16uB9FuRoDvv5-EmpIJydX7QjoPM4Ttf1/view?usp=share_link | Both | Functionality | Feedback
| Contact Us | Faq | Animated Design | Should be hidden. | https://drive.google.com/file/d/15W-YtuPeh5nzEKarAB3DEb6O9m0XS32F/view?usp=sharing | Both | Design | Feedback
|  |  | Toggle Icon | Toggle icon is (-) by default for all | https://drive.google.com/file/d/1AgnCpSt9z8FYGOYH2LIr0pSDmjdwPKUD/view?usp=sharing | Both | Design & Functionality | Bug
| Search |  | Cross Icon | Cross icon is not located next to search bar. | https://drive.google.com/file/d/1sINvFiBiVSNyOyIkbBEA0c2M8rSbwtxa/view?usp=share_link | Both | Design & Functionality | Bug
| Services | Influencers | How Marvel Works | Even if an image is provided from backend, it is not displayed on the frontend. |  | Both | Functionality | Bug
|  | Slider Image |  | Even if an image is provided from backend, it is not displayed on the frontend. |  | Both | Functionality | Bug
MNC | Specific profile | Profile Edit | Inluencer Campaigns | While removing it will show "Do you want to remove?" | https://drive.google.com/file/d/1WpFI-AEsVMD0m18MTUaDsRonFgonN2nA/view?usp=share_link | Both | Functionality | Feedback

## pending
Section | Page | Item | Sub Item | Description | Reference | Platform | Type | Feedback/Bug/CR | Dev Status | Comments
| Home Page | Be Marvel Be you | Cover Image | Position will be same as figma. Currently cover image overlaps with the text. |  | Both | Design & Functionality | Bug | Done & Informed
|  | Get the latest news | Allignment | should follow figma | https://drive.google.com/file/d/1f1mV_TKuCzE3LRLvFQVq4yfMTuUzRX84/view?usp=share_link | Both | Design | Feedback | Done & Informed | .
|  | Testimonials | Enayet Chowdhury | Design breaks. please keep the same background for all the testimonials | https://drive.google.com/drive/folders/1vmL09EypsgBjzenSB4O1E-r4nNH6BNOP?usp=share_link | Both | Design & Functionality | Bug | Done & Informed
|  | Trsuted By | Cards | All cards should be clickable. | https://drive.google.com/drive/folders/1XndDgkMpTkuTC1EDE__7NApP4j1j4J08?usp=share_link | Both | Design | Bug | Done & Informed
|  | Cover Video | - | Video upload option should be implemented from backend. Currently only youtube video uploading is allowed. | https://drive.google.com/file/d/16uB9FuRoDvv5-EmpIJydX7QjoPM4Ttf1/view?usp=share_link | Both | Functionality | Feedback | Done
| Contact Us | Faq | Animated Design | Should be hidden. | https://drive.google.com/file/d/15W-YtuPeh5nzEKarAB3DEb6O9m0XS32F/view?usp=sharing | Both | Design | Feedback | Done & Informed
|  |  | Toggle Icon | Toggle icon is (-) by default for all | https://drive.google.com/file/d/1AgnCpSt9z8FYGOYH2LIr0pSDmjdwPKUD/view?usp=sharing | Both | Design & Functionality | Bug | Done
| Search |  | Cross Icon | Cross icon is not located next to search bar. | https://drive.google.com/file/d/1sINvFiBiVSNyOyIkbBEA0c2M8rSbwtxa/view?usp=share_link | Both | Design & Functionality | Bug | Done
| Services | Influencers | How Marvel Works | Even if an image is provided from backend, it is not displayed on the frontend. |  | Both | Functionality | Bug | Done & Informed | .
|  | Slider Image |  | Even if an image is provided from backend, it is not displayed on the frontend. |  | Both | Functionality | Bug
MNC | Specific profile | Profile Edit | Inluencer Campaigns | While removing it will show "Do you want to remove?" | https://drive.google.com/file/d/1WpFI-AEsVMD0m18MTUaDsRonFgonN2nA/view?usp=share_link | Both | Functionality | Feedback | Done | .
All | Home page | Images | - | Picture brushing should be implemented |  | Both | Design | Feedback
|  | Edit Profile | - | Need to be visible & eye catching |  | Both | Design & Functionality | Feedback | Done
Influencer | Edit Profile | Social Media Presence | Field Asterisks | Should be visible for mandatory fields |  | Both | Design & Functionality | Feedback | Done | .
- | Home Page | Video |  | Even if an video is provided from backend, it is not displayed on the frontend. |  | Both | Functionality | Bug | Done | .
- |  | Profile Icon | - | edit profile , complete profile , logout functions will be included in this. Profile picture will be shown here as well. |  | Both | Design & Functionality |  | Done
Master Brand |  | Create Job | Budget for next 1 year | there will be predefined range. | Range: 10000-50000 50000-100000 100000-150000 150k+ | Both | Design & Functionality | CR | Done
Influencer | Edit Profile | Social Media Presence | Field Asterisks | Should be visible for mandatory fields |  | Both | Design & Functionality | Feedback | Done
All | Home page | Testimonials | - | Background colour will be changed.Clicking on a specific testimonial will be changed to light green colour. other testimonials will be white. |  | Both | Design | Feedback | Done
|  |  | - | Testimonials will be used as sliders. No video section will be there |  | Both | Design & Functionality | Feedback
| Services | Dropdown |  | There will be another category in the dropdown named "Our Flagship Programs". Clicking on that will be redirected to a sub menu. ref : http://themarvel.com/ |  | Both | Design & Functionality | Feedback | Done
All | Responsiveness |  |  | Need to work on responsiveness | https://drive.google.com/drive/folders/1NuCCRrJ7tBBaDkIWnyEK6-3deCbbW-3N?usp=share_link | Mobile,Iphone,Web |  | Bug

## 15.05.2023
Section | Page | Item | Sub Item | Description | Reference | Platform (Mobile, Web, Iphone) | Feedback/Bug/CR | Dev Status | UAT Status
All | Home | Footer | Get the latest news | It will be "Get The Latest News" |  | All | Feedback | Done
| Services | Brand | Testimonial | Will be Brand Testinmonial |  | Phone | Feedback | Dne
|  | Influencer |  | Will be Influencer Testimonial |  | Phone | Feedback | Done
|  | Brand & Influencer |  | If no pictures are uploaded for the testiminials or no logos are provided from the backend it will be blank |  | All |  | Backend
| Blogs | Share on social media | Social Media colour | should be original |  | All | Feedback | Done
| Hamburger menu | Social media icons |  | needs to be original & Instagram should be added as social media just like web |  | Web | Bug | Done | Frontend Part Done
| Influencer | My profile | Profile picture | Profile picture needs to be shown below cover photo | https://drive.google.com/drive/folders/1yrGXBGysepF44kG1l9yp5QI8Wh-fNa09?usp=share_link | Mobile & Iphone | Feedback | Done
|  | Profile Edit | About | This section should not exceed 300 words. | https://drive.google.com/drive/folders/1yrGXBGysepF44kG1l9yp5QI8Wh-fNa09?usp=share_link | All | Feedback | Backend
|  | profile | Category | Only 2 Category is visible in profile through more than 2 Category was added. | https://drive.google.com/drive/folders/1DlHyJEqzEV1_TVWATlmEC6O_4C7NMWxU?usp=share_link | All | Feedback | Backend
|  | Analytics & My profile | Last 1 year of major brands worked with | From where rose & daraz are showing! should not the brands name same?Adding the brand name in profile edit option is not showing the exact brand names. | https://drive.google.com/drive/folders/1R_CoUxR4pIpilesum5cT76mvFzFF7Weq?usp=share_link | All | Feedback | Backend
All | Phone Number | Validation |  | Phone number validation needs to be implemented |  | All | Feedback | Backend
| Home | At a glance | Pictures | All pictures of the influencers need to be shown. Currently only 3 pictures are visible |  | Iphone & Mobile | Bug | Done
All | Blogs | Cover Image |  | Cover Image Auto crops.Clicking on the read more it expands automatically. It should be handled | https://drive.google.com/drive/folders/1bKBcI-KbsMmw1U60kH6TCGYoV0eZoFYp?usp=share_link | All | Feedback | Need to upload - "2560 × 570" px - image size from backend

## 17.05.23
Page | Item | Sub Item | Description | Reference | Platform | Feedback/Bug | Dev Comments | QA Comment
OTP Varification Page | Nav Bar | Marvel Logo | The marvel logo moves to the right side of the nav bar. | https://drive.google.com/file/d/19I9evbdh9Sij8i7o0pIgya_IcbaOO0q7/view?usp=share_link | Iphone/android | Bug | Done (C) | Done
| Menu bar | Notification Bell | The notification bell is not working properly and the notification window should be alingned properly | https://drive.google.com/file/d/1b2Q8Ep91wY1TIydpVrIVxKSro0se2yZU/view?usp=share_link | Iphone | Bug | Done (C) | Done
All Pages | Footer section | Blogs and news, Faq, Contact us | Blogs and news, Faq, Contact us button should be aligned | https://drive.google.com/file/d/100wTGRwG9zHRfyC528UGTV4dd3KhUjwc/view?usp=share_link | Iphone/android | Feedback | Done (C) | Done
Edit My Profile | Placeholder |  | After successfully signup to a profile the placeholder should show "Please Complete Your Profile" | https://drive.google.com/file/d/19NWrVk86abgyuBS0sqRl4un_M-NsL53Z/view?usp=share_link | Iphone/android | Feedback | BE | Done
HOmepage | The Marvel Be You |  | The space between "Be Marvel Be You" and Nav bar should be reduced | https://drive.google.com/file/d/175OKXplFit8SFseADhg0-vB0cKtAw5Mf/view?usp=share_link | Iphone/android | Feedback | Done (C) | Done
SME Profile | My profile | Name | The profile name is overlapping with the profile picture | https://drive.google.com/file/d/1hwpp_CfmtJ-FDGkF0SjQp26SW4uzry-I/view?usp=share_link | Iphone/android | Bug | Done | Done
SME/Influencer Profile | Edit Profile | Phone number | Even after editing new phone number from the edit pro file ,the phone number is not changing. |  | Iphone/android | Bug | BE | Done
MNC Brand | Edit Profile |  | After clicking the submit button the system is not redirecting to my profile |  | Web/iphone/ android | bug | BE | Done
SME Profile | My profile | Email Address | The email address card is not responsive | https://drive.google.com/file/d/1BhdBx26-SmbUaMiAdfVco4HtIHWuSxdf/view?usp=share_link | Iphone/android/Web | Bug | Done | Done
Master Brand Profile | My profile | Location card | The card is not responsive | https://drive.google.com/file/d/1w4KZA_Ku5xbE-ZrLTQ-ZU0oxJJU8Qvyl/view?usp=share_link | Web | Bug | Done | Done
Master Brand Profile | My profile | Email card | The card is not responsive | https://drive.google.com/file/d/1Q2Xu99uoZt8034ULDBzGsMPGI2LhdSo7/view?usp=share_link | Web | Bug | Done | Done
Master Brand Profile | Analytics |  | Reduce the space between profile picture and your campaign | https://drive.google.com/file/d/1-Nk9lBdwV89VX-CZbth9DwEbO2Gs3WFS/view?usp=sharing | Web | Feedback | Done | Done
MNC Brand | Analytics |  | Reduce the space between profile picture and your campaign |  | Web | Feedback | Done | Done

## 22.05.23
Section | Page | Item | Sub Item | Description | Reference | Platform (Mobile, Web, Iphone) | Feedback/Bug/CR | Dev Status | UAT Status
All | Services | Influencer | Banner Image | Auto crops in mobile view. Need to fix the responsiveness | https://drive.google.com/drive/folders/1N-LONlk1ovbEqVYRwXFzf1d4F1AB9uZ3?usp=share_link | Mobile | Bug | Done
All | Home | Join as brand |  | Join as brand will be Join as Advertiser. Also reduce the spacing. | https://drive.google.com/file/d/1ykmmwvUSQo2FBAuefS7ivhRK5a_rs5Nx/view?usp=share_link | All | Feedback | Done
All | All | Footer | Copy right text | should be bold & black. |  | All | Feedback | Done
All | Services | Trusted By | Join as advertiser | Is not responsive | https://drive.google.com/file/d/1Vx2zkgm438q4quPw3GoNdEEyKYumdyyr/view?usp=share_link | All | Bug
All | Blogs & news | Text colour |  | Text colour can be changed from backend. |  | All | Feedback | Done
Specific Profile | Home |  |  | While logged into a specific profile join as influencer & join as brand button will be invisible. |  | All | Feedback | Done
All | Services | Brand Testimonial |  | Does not slide. |  | Mobile | Bug | Done
|  | Influencer Testimonial | [5 empty] | Done
All | Home | Brand Testimonial |  | Does not slide. |  | Mobile | Bug | Done
All | Home | Scroll down |  | Place the field below the home slider. |  | Mobile | Feedback | Done

## 23.05.23
Section | page | Task | Subtusk | Description | Reference | Platfrom (mobile,iphone,web) | Type | Dev Comment
| Blogs | Read More | Banner image | Needs to fix the responsiveness | https://drive.google.com/file/d/1dPCV1bnrGaVuQ6HkKkSZ9R3JMhUoqHxK/view?usp=share_link | Mobile & Iphone | Bug | Done
|  |  | Title | Title front size need to reduce | https://drive.google.com/file/d/1lwENh_SbrMlPuosIONVLWIHMEepJHHSy/view?usp=share_link | Mobile & Iphone | Feedback | Done
Influencer | profile |  |  | this section sholud be add above audience brackdown | https://drive.google.com/file/d/1YnygQG-pzRh9ic4YnbVGvOwR3e3-aTEJ/view?usp=sharing | Mobile & Iphone | Feedback | Done
service | Influencer List | profile |  | Reduce the space between about and age & age and last one year major brand work with | https://drive.google.com/file/d/1488YjgMdOThqrGhWGgmrXbpnqTIbHT2O/view?usp=sharing | Mobile & Iphone | feedback | Done
|  |  |  | want more informations?click, this line sholud be show in middle | https://drive.google.com/file/d/12whx0Ffwe97OZXY6ZkZ-nqYOUuUPpR_I/view?usp=sharing | mobile and iphone |  | Done
ALL | Home | Banner image |  | After clicking on scroll down alarm image should be appear as round shape. | https://drive.google.com/file/d/1Y6cM4aKzDTBFvC92VPSMLLEp8XJi6h6u/view?usp=sharing | All | Feedback | Done
All | Specific Blogs | Title |  | Title will not be visible on the blog image for mobile view. Will be shown below the blog image |  | Mobile,Iphone | Feedback | Done
All | Services | Brand | Alignment | Needs to be fixed | https://drive.google.com/file/d/1uxMMCsZhLgSUz97bOiSmeUd91vBfFUo_/view?usp=share_link | All | Bug | Done
|  | Influencer | [5 empty] | Done